## Sheet1
TASKS | Subtasks | Estimates (hrs) | Queries/Explanation
Design the Mobile Screens |  | 40
Design web dashboard screens |  | 24
Database and Design Architecture Design |  | 16
Setup
| Setting Up Mobile App(APIs,Redux,etc) | 12
| Setting Up Backend | 8
| Designing Database | 16 | as there are different groups of users
| Setting Up Admin Panel | 6
Services
| On the spot fixing | 20 | For on the spot fixing do we need to contact some pre decideds mechanics or would these be from the users of the app registered as mechanics
| Link up with alternate car hailing system | 24 | Is this going to be linked to services like uber/lyft or we'll send the notification to nearby available users
| Towing requests | 12
| Road Traffic news alerts(Frontend and Backend) | 28 | are we going to use traffic alerts provided by users? as using google's api and continously checking it does'nt seem feesible and the users can be in many different cities
| Vehicle maintanaince tips | 8
| Route directions | 16
| Bus Stop designations | 6
| Link up with insurances(frontend and backend) | 8 | Is this only keeping track of the insurance inforamtion?
| Vehicle inspection and insurance Certification | 6
Managing Users
| Sign up/Register functionality for all types of users | 20
| Login functionality | 8
| Social Media Auth | 10
| Profile management | 20 | Is the app going to have same flow for all the users the time for all the above might increase/decrease depending on those
| Profile Page Ui | 10
| Password management(forgot/reset) | 8
| Requests of Users in multiple formats | 12
ALerts System
| Trigger and Broadcast alerts to all users | 12 | Are all these alerts going to be notifications of a specific feed
| Traffic related broadcasts | 8 | depends on what are the requirements
Calender Events |  |  | Not described! following are guesses
| Schduling car health checks | 12 | this is if we keep in mind both the mechanics and the user
| Scheduling for car maintanence/repair | 12
General Features
| Push Notifications | 16
| User Search | 12
| User Search Ui | 8
| In app purchases/financial transactions | 32 | In app purchases won;t take time but implementing transactions will
| Offline Feature to view notifications | 8 | we will be able to store the old notifications and show them as a feed
| App analytics | 10 | can be done using firebase crashlytics
Chats
| Feature to chat with users | 6
| Making chat rooms(ui) | 8
| handling backend part of the chats | 16
Admin Panel
| Sending Notifications | 8
| Main dashboard with some analytics | 16
| Users data tables | 20 | as there are different types of users
| Traffic related data | 10
| Operations on users(edit /delete) | 10
Testing QA rounds |  | 20
Deployment and Deliverables |  | 15
| Total | 562